## Gantt Chart
Project CyberBlock
Development Team Members: Ridhisha Dangol Zachary Kelly Nelson Lau Xin Jason Li | Color Legend: Categories - Grey Ridhisha - Gold Zach - Green Nelson - Blue Jason - Red Client - Purple All team members - Brown | Start date: 16-Jan-2022 End date: 10-May-2022
[6 empty] | Week #1 | [6 empty] | Week #2 | [6 empty] | Week #3 | [6 empty] | Week #4 | [6 empty] | Week #5 | [6 empty] | Week #6 | [6 empty] | Week #7 | [6 empty] | Week #8 | [6 empty] | Week #9 | [6 empty] | Week #10 | [6 empty] | Week #11 | [6 empty] | Week #12 | [6 empty] | Week #13 | [6 empty] | Week #14 | [6 empty] | Week #15 | [6 empty] | Week #16 | [6 empty] | Week #17
 | time axis 2022-01-16 to 2022-05-14
Task | Description | Member | Progress | Start | End | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
1 - Planning |  | Category |  | 2022-01-16 | 2022-02-02
1.1 - Documentation | Requirements Document Revision 3 | Team | Complete | 2022-01-18 | 2022-01-25
1.1 - Documentation | Requirements Document Revision 4 | Nelson | Complete | 2022-01-30 | 2022-02-05
1.2 - Mockups | Create Layout Mockup | Zachary | Complete | 2022-01-24 | 2022-01-27
1.2 - Mockups | Create Design & Color Mockups | Zachary | Complete | 2022-01-27 | 2022-02-03
2 - UI/UX Changes |  | Category |  | 2022-02-03 | 2022-02-19
2.1 - Revise UI | Add crown to leaderboard | Ridhisha | Complete | 2022-01-23 | 2022-01-29
2.1 - Revise UI | Implement Mock-Up Design to Game | Team | Complete | 2022-01-30 | 2022-02-26
2.1 - Revise UI | Apply Color Palette | Team | Complete | 2022-02-06 | 2022-02-12
2.1 - Revise UI | Change homepage | Nelson | Complete | 2022-02-06 | 2022-02-12
2.1 - Revise UI | Add navigation bar | Zachary | Complete | 2022-02-08 | 2022-02-12
3 - Initial Debugging |  | Category |  | 2022-02-03 | 2022-02-19
3.1 - Fix initial Bugs | Fixing initial bugs from the demo run | Jason | Complete | 2022-01-23 | 2022-02-05
4 - Testing |  | Category |  | 2022-02-20 | 2022-03-19
4.1 - User Testing Plan | Planning | Team | Complete | 2022-02-20 | 2022-03-05
4.1 - Complete Testing Plan | Complete Testing plan | Category | Complete | 2022-03-01 | 2022-03-01
4.2 - User Testing |  | Team | Complete | 2022-03-06 | 2022-03-19
4.3 - Implement Changes | Impement User Testing Comments | Team | Complete | 2022-03-06 | 2022-04-09
4.3.1 - Database Revisions | Implement the new database | Nelson | Complete | 2022-04-05 | 2022-04-07
4.3.1.1 - Database Revisions | Remove Duplicates | Nelson | Complete | 2022-04-14 | 2022-04-15
4.3.2 - Chat button can send even if there is nothing in it | Don't allow users to send nothing | Nelson | Complete | 2022-04-08 | 2022-04-09
4.3.3 - Chat send message with enter | Press enter to send message | Nelson | Complete | 2022-04-11 | 2022-04-13
4.3.4 - Restriction for rejoining and disconnection handling |  | Jason | Complete | 2022-04-01 | 2022-04-04
4.3.5 - Purchased defense didn't show up or in wrong place |  | Jason | Complete | 2022-04-04 | 2022-04-07
4.3.6 - Host cannot advance to the next round until every team has submitted their defenses |  | Jason | Complete | 2022-04-07 | 2022-04-10
4.3.7 - scroll bar issues | scrolll is causing problems in different screens | Ridhisha | Complete | 2022-04-05 | 2022-04-10
4.3.8 -show all game details | all the game details like players, defenses etc need to be shown | Ridhisha | Complete | 2022-04-05 | 2022-04-10
4.3.9 - UI Changes to Players | Change players are displayed before game | Zachary | Complete | 2022-04-04 | 2022-04-06
4.3.10 - UI Changes to Trivia | Make trivia styling consistent | Zachary | Complete | 2022-04-06 | 2022-04-08
4.3.11 - Instructions | Add instructions to homepage | Zachary | Complete | 2022-04-11 | 2022-04-12
4.3.12 - Logging | Add more logging | Jason | Complete | 2022-04-11 | 2022-04-14
4.3.13 - Feature Enhancement | Suggest defense during gameplay | Jason | Complete | 2022-04-14 | 2022-04-17
4.3.14 - Feature Enhancement | Clear selected defenses during gameplay | Jason | Complete | 2022-04-14 | 2022-04-17
4.3.15 - Feature Enhancement | Show lobby an alert when host gets disconnected | Jason | Complete | 2022-04-14 | 2022-04-17
4.3.16 - Feature Enhancement | Error handling for 10th trivia question | Jason | Complete | 2022-04-14 | 2022-04-17
4.3.17 - Feature Enhancement | Show alert when there is a team leader switch | Jason | Complete | 2022-04-14 | 2022-04-17
4.3.18 - Bug Fix | Update everybody’s money after trivia | Jason | Complete | 2022-04-14 | 2022-04-17
4.4 - Improvement Presentation | Present testing improvements | Team | Complete | 2022-03-27 | 2022-04-09
4.5 - Re-testing | Test again | Team | Complete | 2022-04-10 | 2022-04-16
4.6 - Final changes | Finally deploy the implemented changes | Team | Complete | 2022-04-17 | 2022-04-23
Spring break | Spring break | Category | Complete | 2022-03-20 | 2022-03-26
5 - Deployment |  | Category |  | 2022-04-21 | 2022-05-13
5.1 - Present Wrap Up Plan |  | Team | Complete | 2022-04-24 | 2022-04-30
5.2 - Documentation Round-Up |  | Team | Complete | 2022-04-24 | 2022-04-30
5.3 - Demo to Client |  | Team | Complete | 2022-05-01 | 2022-05-07
5.4 - Technology Transfer |  | Team | Complete | 2022-05-01 | 2022-05-07
6 - Class Activities |  | Category |  | 2022-05-01 | 2022-05-14
6.1 - Final Presentation |  | Team | Complete | 2022-05-01 | 2022-05-14
6.2 - Competition |  | Team | Complete | 2022-05-08 | 2022-05-14
Insert Cells Above This Cell

## OLD CHART
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17
Task Name | 01/16-01/22 | 01/23-01/29 | 01/30-02/05 | 02/06-02/12 | 02/13-02/19 | 02/20-02/26 | 02/27-03/05 | 03/06-03/12 | 03/13-03/19 | 03/20-03/26 | 03/27-04/02 | 04/03-04/09 | 04/10-04/16 | 04/17-04/23 | 04/24-04/30 | 05/01-05/07 | 05/08-05/14
Requirements Specification Version 3 | bar: Week 1 to Week 2
Mock-Up User Interface | bar: Week 1 to Week 2
Add Crown Feature to Leaderboard | bar: Week 2
Debug Existing Problems from Client Testing | bar: Week 2 to Week 3
Requirements Specification Version 4 | bar: Week 3
Implement Mock-Up Design to Game | bar: Week 3 to Week 6
Apply Color Palette | bar: Week 4
User Testing Plan | bar: Week 6 to Week 7
User Testing | bar: Week 8 to Week 9
Implement User Testing Comments | bar: Week 8 to Week 12
Testing Improvement Presentation | bar: Week 11 to Week 12
Re-Testing | bar: Week 13
Final Deployment and Demonstrations | bar: Week 14
Present Project Wrap Up Plan | bar: Week 15
Documentation Roundup | bar: Week 15
Demo Final Product to Client | bar: Week 16
Technology Transfer to Client | bar: Week 16
Final Presentation | bar: Week 16 to Week 17
Senior Design Competition | bar: Week 17
Zach | bar: Week 1
Jason | bar: Week 1
Ridhisha | bar: Week 1
Nelson | bar: Week 1
Client | bar: Week 1
All Team Members | bar: Week 1