## Nelson
Requirement | Task | Date | Start Time | End Time | Minutes Elape | Task Due Date | Task Actual Date Completed
Software Requirements Specifications | Separate the sections to each team members | 2021-09-07 | 20:47 | 21:34 | 47 | ASAP | 2021-09-23
Software Requirements Specifications | Completed the introduction, purpose, and references | 2021-09-08 | 16:17 | 17:54 | 97 | ASAP | 2021-09-23
Team Agenda | Schedule meeting and questions and talking points | 2021-09-09 | 9:58 | 10:44 | 46 | 2021-09-09 | 2021-09-09
Team Agenda | participated in a client meeting | 2021-09-09 | 16:30 | 17:04 | 34 | 2021-09-09 | 2021-09-09
Team Agenda | Schedule meeting and questions and talking points | 2021-09-12 | 9:13 | 9:29 | 16 | 2021-09-12 | 2021-09-13
Team Agenda | participated in a client meeting | 2021-09-13 | 12:30 | 13:02 | 32 | 2021-09-13 | 2021-09-13
Team Agenda | Schedule meeting for the game demo | 2021-09-14 | 2:17 | 2:52 | 35 | 2021-09-16 | 2021-09-14
Team Agenda | participated in a team meeting | 2021-09-16 | 15:41 | 16:51 | 70 | 2021-09-16 | 2021-09-16
Software Requirements Specifications | Completed the scope and added to the references | 2021-09-18 | 17:51 | 18:43 | 52 | ASAP | 2021-09-23
Software Requirements Specifications | Added to the references | 2021-09-19 | 21:50 | 22:30 | 40 | ASAP | 2021-09-23
Software Requirements Specifications | Completed the feature, stimulus, and response | 2021-09-21 | 21:57 | 23:08 | 71 | ASAP | 2021-09-23
Software Requirements Specifications | Completed the functional hierarchy and added to the definitions | 2021-09-22 | 20:29 | 21:35 | 66 | ASAP | 2021-09-23
Software Requirements Specifications | Formattting | 2021-09-23 | 21:34 | 23:10 | 96 | ASAP | 2021-09-23
Software Requirements Specifications | Finished Formattting the document | 2021-09-24 | 14:02 | 20:00 | 358 | ASAP | 2021-09-23
Team Agenda | Schedule meeting and questions and talking points | 2021-09-26 | 9:28 | 9:50 | 22 | 2021-09-26 | 2021-09-27
Team Agenda | participated in a client meeting | 2021-09-27 | 12:30 | 13:02 | 32 | 2021-09-27 | 2021-09-27
Research | AWS | 2021-09-28 | 19:37 | 20:56 | 79 | 2021-09-28 | 2021-09-30
Team Agenda | Schedule meeting and questions and talking points | 2021-09-29 | 22:23 | 22:52 | 29 | 2021-09-29 | 2021-09-30
Team Agenda | participated in a team meeting | 2021-09-30 | 16:30 | 17:00 | 30 | 2021-09-30 | 2021-09-30
Client Meeting Presentation | Completed the web service options | 2021-10-03 | 14:19 | 15:04 | 45 | 2021-10-03 | 2021-10-04
Client Meeting Presentation | Completed the database options | 2021-10-03 | 20:00 | 20:50 | 50 | 2021-10-03 | 2021-10-04
Team Agenda | participated in a client meeting | 2021-10-04 | 12:30 | 13:00 | 30 | 2021-10-04 | 2021-10-04
Team Agenda | participated in a team meeting | 2021-10-07 | 16:30 | 17:00 | 30 | 2021-10-07 | 2021-10-07
Team Agenda | participated in a client meeting | 2021-10-11 | 12:30 | 13:00 | 30 | 2021-10-11 | 2021-10-11
Gantt Chart | Added to the Gantt chart | 2021-10-11 | 17:23 | 18:07 | 44 | ASAP | ASAP
Team Agenda | participated in a team meeting | 2021-10-14 | 16:30 | 17:00 | 30 | 2021-10-14 | 2021-10-14
Gantt Chart | Added to the Gantt chart | 2021-10-14 | 17:34 | 18:09 | 35 | ASAP | ASAP
Team Agenda | participated in a client meeting | 2021-10-18 | 12:30 | 13:20 | 50 | 2021-10-18 | 2021-10-18
ER Diagram | Create a prototype ER Diagram | 2021-10-20 | 15:40 | 17:16 | 96 | 2021-10-20 | 2021-10-20
Team Agenda | participated in a team meeting | 2021-10-21 | 16:30 | 17:00 | 30 | 2021-10-21 | 2021-10-21
Design Document | Introduction and Overview | 2021-10-24 | 19:04 | 21:37 | 153 | 2021-10-25 | 2021-10-26
Team Agenda | participated in a client meeting | 2021-10-25 | 12:30 | 13:05 | 35 | 2021-10-25 | 2021-10-25
MySQL | Research and tutorials | 2021-10-26 | 12:15 | 15:12 | 177 | 2021-10-26 | 2021-10-31
Design Document | Formattting | 2021-10-26 | 19:25 | 21:18 | 113 | 2021-10-25 | 2021-10-26
MySQL | Attack and Defense table | 2021-10-27 | 18:43 | 21:47 | 184 | 2021-10-27 | 2021-10-31
Team Agenda | participated in a team meeting | 2021-10-28 | 16:30 | 17:00 | 30 | 2021-10-28 | 2021-10-28
Design Document | Finished Formattting the document | 2021-10-28 | 20:09 | 22:22 | 133 | 2021-10-25 | 2021-10-26
MySQL | Finished beginner Attack, Defense, and Wildcard table | 2021-10-31 | 16:04 | 19:52 | 228 | 2021-10-31 | 2021-10-31
Team Agenda | participated in a client meeting | 2021-11-01 | 12:30 | 13:00 | 30 | 2021-11-01 | 2021-11-01
Team Agenda | participated in a team meeting | 2021-11-04 | 16:30 | 17:00 | 30 | 2021-11-04 | 2021-11-04
MySQL | Transfer Local Database to Remote | 2021-11-07 | 12:42 | 13:53 | 71 | 2021-11-07 | 2021-11-07
Code Testing | Testing MySQL Connection in Node.js | 2021-11-07 | 18:56 | 21:55 | 179 | 2021-11-07 | 2021-11-07
Team Agenda | participated in a client meeting | 2021-10-08 | 12:30 | 13:00 | 30 | 2021-11-08 | 2021-11-08
Coding | Implementing MySQL connection to server side | 2021-11-09 | 17:30 | 18:12 | 42 | 2021-11-09 | 2021-11-12
Coding | Creating MySQL commands | 2021-11-10 | 16:17 | 18:06 | 109 | 2021-11-10 | 2021-11-12
Team Agenda | participated in a team meeting | 2021-11-11 | 16:30 | 17:00 | 30 | 2021-11-11 | 2021-11-12
Coding | Creating MySQL commands | 2021-11-12 | 13:48 | 16:00 | 132 | 2021-11-12 | 2021-11-12
Team Agenda | participated in a client meeting | 2021-11-15 | 12:30 | 13:00 | 30 | 2021-11-15 | 2021-11-15
Team Agenda | participated in a team meeting | 2021-11-18 | 16:30 | 17:00 | 30 | 2021-11-18 | 2021-11-18
MySQL | Creating MySQL commands | 2021-11-21 | 13:00 | 14:14 | 74 | 2021-11-21 | 2021-11-21
MySQL | Created points table | 2021-11-23 | 14:15 | 21:37 | 442 | 2021-11-23 | 2021-11-23
Team Agenda | participated in a client meeting | 2021-11-29 | 12:30 | 13:00 | 30 | 2021-11-29 | 2021-11-29
MySQL | Creating MySQL queries | 2021-11-30 | 13:42 | 18:37 | 295 | 2021-11-30 | 2021-11-30
MySQL | Added more elements to tables | 2021-11-30 | 18:52 | 0:13 | 321 | 2021-11-30 | 2021-11-30
Team Agenda | participated in a team meeting | 2021-12-03 | 16:30 | 17:00 | 30 | 2021-12-03 | 2021-12-03
Coding | Implemented MySQL queries to code | 2021-12-03 | 19:00 | 21:04 | 124 | 2021-12-03 | 2021-12-03
Team Agenda | participated in a client meeting | 2021-12-06 | 12:30 | 13:00 | 30 | 2021-12-06 | 2021-12-06
MySQL | Changed some cost values | 2021-12-06 | 18:52 | 7:30 | 38 | 2021-12-06 | 2021-12-06
Team Agenda | participated in a team meeting | 2021-12-09 | 16:30 | 17:00 | 30 | 2021-12-09 | 2021-12-09
Presentation | Revised Presentation to add challenges | 2021-12-12 | 17:37 | 21:20 | 223 | 2021-12-12 | 2021-12-12
Team Agenda | participated in a team meeting | 2022-01-20 | 10:00 | 10:30 | 30 | 2022-01-20 | 2022-01-20
Team Agenda | participated in a client meeting | 2022-01-20 | 10:30 | 11:30 | 60 | 2022-01-20 | 2022-01-20
Software Requirements Specifications | Adding the UI and UX | 2022-01-23 | 18:34 | 21:10 | 156 | 2022-01-25 | 2022-01-25
Software Requirements Specifications | Editing the UI and UX | 2022-01-25 | 17:25 | 18:30 | 55 | 2022-01-25 | 2022-01-25
Team Agenda | participated in a team meeting | 2022-01-27 | 10:00 | 10:30 | 30 | 2022-01-27 | 2022-01-27
Team Agenda | participated in a client meeting | 2022-01-27 | 10:30 | 11:30 | 60 | 2022-01-27 | 2022-01-27
Gantt Chart | Semester 2 | 2022-01-30 | 18:37 | 20:08 | 91 | 2022-02-01 | 2022-02-01
Team Agenda | participated in a team meeting | 2022-02-03 | 10:00 | 10:30 | 30 | 2022-02-03 | 2022-02-03
Team Agenda | participated in a client meeting | 2022-02-03 | 10:30 | 11:30 | 60 | 2022-02-03 | 2022-02-03
Material UI Review | Learn Material UI | 2022-02-08 | 10:03 | 3:12 | 309 | 2022-02-12 | 2022-02-12
Team Agenda | participated in a team meeting | 2022-02-10 | 10:00 | 10:30 | 30 | 2022-02-10 | 2022-02-10
Team Agenda | participated in a client meeting | 2022-02-10 | 10:30 | 11:30 | 60 | 2022-02-10 | 2022-02-10
Color Implementation | Implement client colors into LobbyInterface and HostConfiguration | 2022-02-12 | 14:17 | 16:02 | 105 | 2022-02-16 | 2022-02-16
UI and UX | Implement input sanitization and required fields | 2022-02-13 | 11:24 | 14:00 | 156 | 2022-02-16 | 2022-02-16
UI and UX | Implement input sanitization and required fields | 2022-02-14 | 15:00 | 17:28 | 148 | 2022-02-16 | 2022-02-16
Team Agenda | participated in a team meeting | 2022-02-17 | 10:00 | 10:30 | 30 | 2022-02-17 | 2022-02-17
Team Agenda | participated in a client meeting | 2022-02-17 | 10:30 | 11:30 | 60 | 2022-02-17 | 2022-02-17
MySQL | Change point values assigned to corresponding defenses | 2022-02-23 | 14:34 | 17:17 | 163 | 2022-03-04 | 2022-02-23
Team Agenda | participated in a team meeting | 2022-02-24 | 10:00 | 10:30 | 30 | 2022-02-24 | 2022-02-24
Team Agenda | participated in a client meeting | 2022-02-24 | 10:30 | 11:30 | 60 | 2022-02-24 | 2022-02-24
Instruction Document | Wrote instructions for hosts and players | 2022-02-26 | 13:42 | 16:03 | 141 | 2022-03-01 | 2022-03-01
Survey Questions | Completed Survey Questions for hosts and players | 2022-02-28 | 16:21 | 19:00 | 159 | 2022-03-01 | 2022-03-01
MySQL | Added descriptions to the defenses | 2022-03-02 | 14:32 | 16:00 | 88 | 2022-03-03 | 2022-03-03
Team Agenda | participated in a team meeting | 2022-03-03 | 10:00 | 10:30 | 30 | 2022-03-03 | 2022-03-03
Team Agenda | participated in a client meeting | 2022-03-03 | 10:30 | 11:30 | 60 | 2022-03-03 | 2022-03-03
Survey Questions | Revise questions and reword rating scale | 2022-03-06 | 18:00 | 20:02 | 162 | 2022-03-08 | 2022-03-08
MySQL | Add new defenses and change cost values | 2022-03-06 | 14:17 | 16:50 | 153 | 2022-03-08 | 2022-03-08
MySQL | Worked with Ben to create tables | 2022-03-07 | 17:30 | 18:42 | 72 | 2022-03-08 | 2022-03-08
Teammate Survey | Filling out teammate survey | 2022-03-08 | 13:08 | 14:10 | 62 | 2022-03-08 | 2022-03-08
Team Agenda | participated in a team meeting | 2022-03-10 | 9:15 | 9:45 | 30 | 2022-03-10 | 2022-03-10
Team Agenda | participated in a client meeting | 2022-03-10 | 9:45 | 11:30 | 105 | 2022-03-10 | 2022-03-10
Testing | Testing HuFit | 2022-03-14 | 15:15 | 16:34 | 79 | 2022-03-18 | 2022-03-18
Testing | Testing Social Comparison B | 2022-03-27 | 17:32 | 18:27 | 55 | 2022-03-28 | 2022-03-28
Team Agenda | participated in a team meeting | 2022-03-31 | 10:00 | 10:30 | 30 | 2022-03-31 | 2022-03-31
Team Agenda | participated in a client meeting | 2022-03-31 | 10:30 | 11:30 | 60 | 2022-03-31 | 2022-03-31
Expo Form | Created the abstract | 2022-04-01 | 14:46 | 16:22 | 96 | 2022-03-31 | 2022-03-31
MySQL | Implemented revised database | 2022-04-06 | 13:30 | 17:47 | 257 | 2022-04-07 | 2022-04-07
Team Agenda | Team Agenda | 2022-04-07 | 10:00 | 10:30 | 60 | 2022-04-07 | 2022-04-07
Team Agenda | Team Agenda | 2022-04-07 | 10:30 | 11:30 | 30 | 2022-04-07 | 2022-04-07
Chat Fix | Disable messages sent with nothing | 2022-04-08 | 14:30 | 16:23 | 113 | 2022-04-09 | 2022-04-09
Chat Fix | Disable messages sent with nothing | 2022-04-09 | 14:12 | 15:13 | 61 | 2022-04-09 | 2022-04-09
Chat Fix | Enable users to send messages with enter | 2022-04-13 | 15:04 | 19:39 | 275 | 2022-04-13 | 2022-04-13
Team Agenda | participated in a team meeting | 2022-04-14 | 10:00 | 10:30 | 30 | 2022-04-14 | 2022-04-14
Team Agenda | participated in a client meeting | 2022-04-14 | 10:30 | 11:30 | 60 | 2022-04-14 | 2022-04-14
MySQL | Fix duplicate issue | 2022-04-15 | 19:00 | 20:13 | 73 | 2022-04-17 | 2022-04-17
User Interface | Changed style and font for defense description pop-up | 2022-04-16 | 12:43 | 15:10 | 147 | 2022-04-17 | 2022-04-17
Instruction Document | Revised instructions for hosts and players | 2022-04-17 | 12:39 | 13:24 | 45 | 2022-04-17 | 2022-04-17
Survey Questions | Revised Survey Questions for hosts and players | 2022-04-17 | 13:24 | 16:20 | 176 | 2022-04-17 | 2022-04-17
Testing | Testing Social Comparison B | 2022-04-20 | 13:25 | 14:17 | 52 | 2022-04-20 | 2022-04-25
Team Agenda | participated in a team meeting | 2022-04-21 | 10:00 | 10:30 | 30 | 2022-04-21 | 2022-04-21
Testing | Testing HuFit | 2022-04-23 | 16:32 | 17:35 | 63 | 2022-04-23 | 2022-04-25
Final Presentation | Updated and added testing section | 2022-04-27 | 21:37 | 0:16 | 159 | 2022-04-28 | 2022-04-28
Team Agenda | participated in a team meeting | 2022-04-28 | 10:00 | 10:30 | 30 | 2022-04-28 | 2022-04-28
Team Agenda | participated in a client meeting | 2022-04-28 | 10:30 | 11:30 | 60 | 2022-04-28 | 2022-04-28
Posterboard | Designed Posterboard | 2022-05-03 | 23:30 | 15:10 | 220 | 2022-05-07 | 2022-05-07
Posterboard | Add print to posterboard | 2022-05-04 | 5:30 | 6:32 | 62 | 2022-05-07 | 2022-05-07
Team Agenda | participated in a team meeting | 2022-05-05 | 10:00 | 10:30 | 30 | 2022-05-05 | 2022-05-05

## Zach
Requirement | Task | Date | Start Time | End Time | Minutes | Due Date | Date Completed
SEMESTER 1
Software Requirements | Initial overview and basic research | 2021-09-07 | 19:13 | 19:22 | 0:09 | N/A | 2021-09-07
Team Agenda | Participated in a client meeting | 2021-09-09 | 16:30 | 17:04 | 0:34 | 2021-09-09 | 2021-09-09
Software Requirements | Examined the paper-based version of the game | 2021-09-09 | 17:10 | 17:38 | 0:28 | N/A | 2021-09-09
Team Agenda | Participated in a client meeting | 2021-09-13 | 12:30 | 13:02 | 0:32 | 2021-09-13 | 2021-09-13
Team Agenda | Participated in a game demo | 2021-09-16 | 15:42 | 16:51 | 1:09 | 2021-09-16 | 2021-09-16
Team Agenda | Participated in a client meeting | 2021-09-20 | 12:30 | 13:01 | 0:31 | 2021-09-20 | 2021-09-20
Software Requirements | Completed section of requirements document | 2021-09-23 | 12:47 | 13:36 | 0:49 | 2021-09-23 | 2021-09-23
Team Agenda | Participated in a client meeting | 2021-09-27 | 12:30 | 13:02 | 0:32 | 2021-09-27 | 2021-09-27
Software Requirements | Revised section of requirements document | 2021-09-28 | 17:33 | 18:04 | 0:31 | N/A | 2021-09-28
Team Agenda | Reworked hardware requirements | 2021-09-30 | 17:36 | 17:59 | 0:23 | N/A | 2021-09-30
Team Agenda | Participated in a client meeting | 2021-10-04 | 12:30 | 13:01 | 0:31 | 2021-10-04 | 2021-10-04
Project Planning | Creation of Gantt Chart | 2021-10-05 | 17:24 | 17:31 | 0:07 | N/A | 2021-10-05
Team Agenda | Participated in a client meeting | 2021-10-11 | 12:30 | 12:56 | 0:26 | 2021-10-11 | 2021-10-11
Research | Research game structure and examples | 2021-10-13 | 13:41 | 14:09 | 0:28 | N/A | 2021-10-13
Team Agenda | Participated in a client meeting | 2021-10-18 | 12:30 | 13:21 | 0:51 | 2021-10-18 | 2021-10-18
Design Document | Started working on design document | 2021-10-19 | 17:13 | 18:03 | 0:50 | N/A | 2021-10-19
Software Requirements | Revision of section of requirements document. | 2021-10-21 | 17:10 | 17:56 | 0:46 | N/A | 2021-10-21
Team Agenda | Participated in a client meeting | 2021-10-25 | 12:30 | 13:01 | 0:31 | 2021-10-25 | 2021-10-25
Design Document | Worked on design document | 2021-10-26 | 17:10 | 17:32 | 0:22 | N/A | 2021-10-26
Software Requirements | Revision of section of requirements document. | 2021-10-28 | 16:30 | 17:52 | 1:22 | ASAP | 2021-10-28
Team Agenda | Participated in a client meeting | 2021-11-01 | 12:30 | 13:00 | 0:30 | 2021-11-01 | 2021-11-01
Team Agenda | Participated in a client meeting | 2021-11-08 | 12:30 | 12:49 | 0:19 | 2021-11-08 | 2021-11-08
Team Agenda | Participated in a client meeting | 2021-11-29 | 12:30 | 13:06 | 0:36 | 2021-11-29 | 2021-11-29
Presentation | Worked on final presentation | 2021-12-02 | 14:41 | 16:16 | 1:35 | N/A | 2021-12-02
Coding | Developed chat room | 2021-12-08 | 10:40 | 15:59 | 5:19 | N/A | 2021-12-08
Coding | Developed chat room | 2021-12-09 | 9:22 | 14:50 | 5:28 | N/A | 2021-12-09
Team Agenda | Participated in a client meeting | 2021-12-13 | 12:30 | 13:17 | 0:47 | 2021-12-13 | 2021-12-13
Presentation | Worked on final presentation | 2021-12-13 | 19:34 | 21:01 | 1:27 | N/A | 2021-12-13
Presentation | Worked on final presentation | 2021-12-14 | 11:19 | 13:34 | 2:15 | N/A | 2021-12-14
SEMESTER 2
Team Agenda | Participated in a team meeting | 2022-01-20 | 10:00 | 10:30 | 0:30 | 2022-01-20 | 2022-01-20
Team Agenda | Participated in a client meeting | 2022-01-20 | 10:30 | 11:30 | 1:00 | 2022-01-20 | 2022-01-20
Planning & Documentation | Worked on layout mockup | 2022-01-24 | 17:24 | 18:07 | 0:43 | N/A | 2022-01-24
Team Agenda | Participated in a team meeting | 2022-01-27 | 10:00 | 10:30 | 0:30 | 2022-01-27 | 2022-01-27
Team Agenda | Participated in a client meeting | 2022-01-27 | 10:30 | 11:32 | 1:02 | 2022-01-27 | 2022-01-27
Planning & Documentation | Worked on design mockups | 2022-02-02 | 15:36 | 17:03 | 1:27 | N/A | 2022-02-02
Planning & Documentation | Obtained fonts for font selection | 2022-02-03 | 8:58 | 9:04 | 0:06 | n/A | 2022-02-03
Team Agenda | Participated in a team meeting | 2022-02-03 | 10:00 | 10:30 | 0:30 | 2022-02-03 | 2022-02-03
Team Agenda | Participated in a client meeting | 2022-02-03 | 10:30 | 11:14 | 0:44 | 2022-02-03 | 2022-02-03
Planning & Documentation | Planning & Documentation | 2022-02-07 | 13:23 | 15:23 | 2:00 | N/A | 2022-02-07
Team Agenda | Participated in a team meeting | 2022-02-10 | 10:00 | 10:30 | 0:30 | 2022-02-10 | 2022-02-10
Team Agenda | Participated in a client meeting | 2022-02-10 | 10:30 | 11:35 | 1:05 | 2022-02-10 | 2022-02-10
Learning/Research | Learn More React & Material UI | 2022-02-11 | 10:12 | 11:07 | 0:55 | N/A | 2022-02-11
Team Agenda | Participated in a team meeting | 2022-02-17 | 10:00 | 10:30 | 0:30 | 2022-02-17 | 2022-02-17
Team Agenda | Participated in a client meeting | 2022-02-17 | 10:30 | 11:15 | 0:45 | 2022-02-17 | 2022-02-17
Team Agenda | Participated in a team meeting | 2022-02-24 | 10:00 | 10:30 | 0:30 | 2022-02-24 | 2022-02-24
Team Agenda | Participated in a client meeting | 2022-02-24 | 10:30 | 11:14 | 0:44 | 2022-02-24 | 2022-02-24
Coding | Adjusted/Worked on Lobby UI | 2022-03-02 | 12:34 | 15:31 | 2:57 | 2022-03-02 | 2022-03-02
Team Agenda | Participated in a team meeting | 2022-03-03 | 10:00 | 10:30 | 0:30 | 2022-03-03 | 2022-03-03
Team Agenda | Participated in a client meeting | 2022-03-03 | 10:30 | 11:43 | 1:13 | 2022-03-03 | 2022-03-03
Coding | Fixed merging conflicts | 2022-03-09 | 20:03 | 23:18 | 3:15 | 2022-03-10 | 2022-03-10
Team Agenda | Participated in a team meeting | 2022-03-10 | 9:15 | 9:45 | 0:30 | 2022-03-10 | 2022-03-10
Team Agenda | Pilot Testing Session | 2022-03-10 | 9:45 | 11:19 | 1:34 | 2022-03-10 | 2022-03-10
Team Agenda | Participated in a team meeting | 2022-03-31 | 10:00 | 10:30 | 0:30 | 2022-03-31 | 2022-03-31
Team Agenda | Participated in a client meeting | 2022-03-31 | 10:30 | 11:31 | 1:01 | 2022-03-31 | 2022-03-31
Planning & Documentation | New Items In Gantt Chart | 2022-03-31 | 11:31 | 12:04 | 0.022917 | 2022-03-31 | 2022-03-31
Team Agenda | Participated in a team meeting | 2022-04-07 | 10:00 | 10:30 | 0:30 | 2022-04-07 | 2022-04-07
Team Agenda | Participated in a client meeting | 2022-04-07 | 10:30 | 11:12 | 0:42 | 2022-04-07 | 2022-04-07
Team Agenda | Participated in a team meeting | 2022-04-14 | 10:00 | 10:30 | 0:30 | 2022-04-14 | 2022-04-14
Team Agenda | Participated in a client meeting | 2022-04-14 | 10:30 | 11:59 | 1:29 | 2022-04-14 | 2022-04-14

## Ridhisha
Requirement | Task | Date | Start Time | End Time | Minutes Elape | Task Due Date | Task Actual Date Completed
Software Requirements Specifications | wrote the allocated part of the requirement | 2021-09-07 | 7:45 | 11:12 | 207 min | N/A | 2021-09-18
Team Agenda | participated in a team meeting | 2021-09-09 | 16:30 | 17:04 | 34 min | 2021-09-09 | 2021-09-10
Team Agenda | participated in a team meeting | 2021-09-16 | 15:45 | 16:50 | 65 min | 2021-09-16 | 2021-09-16
Software Requirements Specifications | wrote the allocated part of the requirement | 2021-09-19 | 8:20 | 23:30 | 190 min | N/A | 2021-09-22
Software Requirements Specifications | wrote the allocated part of the requirement | 2021-10-08 | 9:10 | 23:30 | 140 min | N/A | 2021-09-22
Team Agenda | participated in a team meeting | 2021-10-02 | 12:30 | 13:05 | 35 min | 2021-10-02 | 2021-10-02
Team Agenda | participated in a team meeting | 2021-10-17 | 12:30 | 13:10 | 40 min | 2021-10-17 | 2021-10-17
Team Agenda | Team Agenda | 2021-10-14 | 16:30 | 17:00 | 30min | 2021-10-14 | 2021-10-14
Team Agenda | Team Agenda | 2021-10-21 | 16:30 | 17:00 | 30min | 2021-10-21 | 2021-10-21
Requirements Document | wrote the allocated part of the requirement | 2021-10-22 | 11:00AM | 11:40AM | 40mins | ASAP | 2021-10-22
Design documents | wrote the allocated part of the requirement | 2021-10-22 | 12:00PM | 1:00PM | 60mins | ASAP | 2021-10-22
Team Agenda | Participated in a client meeting | 2021-10-25 | 12:30 | 13:01 | 31 | 2021-10-25 | 2021-10-25
Design Document | Worked on design document | 2021-10-26 | 19:30 | 20:10 | 40 | N/A | 2021-10-26
Software Requirements | Revision of section of requirements document. | 2021-10-26 | 20:30 | 21:22 | 52 | ASAP | 2021-10-28
Team Agenda | participated in a client meeting | 2021-11-01 | 12:30 | 13:00 | 30 | 2021-11-01 | 2021-11-01
Team Agenda | participated in a team meeting | 2021-11-04 | 16:30 | 17:00 | 30 | 2021-11-04 | 2021-11-04
coding | work on client side of the project | 2021-11-04 | 12:50 | 4:55PM | 245 | 2021-11-04 | 2021-11-04
Team Agenda | participated in a client meeting | 2021-10-08 | 12:30 | 13:00 | 30 | 2021-11-08 | 2021-11-08
Coding | finishing the buy phase | 2021-11-10 | 11:00AM | 1:00PM | 120 | 2021-11-10 | 2021-11-10
Coding | crete a new interface for game play | 2021-11-11 | 20:12 | 21:30 | 78 | 2021-11-11 | 2021-11-11
Team Agenda | participated in a team meeting | 2021-11-11 | 16:30 | 17:00 | 30 | 2021-11-11 | 2021-11-11
Coding | fix the checkbox in buyphase | 2021-11-12 | 17:34 | 20:10 | 164 | 2021-11-12 | 2021-11-12
Team Agenda | participated in a client meeting | 2021-11-15 | 12:30 | 13:00 | 30 | 2021-11-15 | 2021-11-15
Team Agenda | participated in a team meeting | 2021-11-18 | 16:30 | 17:00 | 30 | 2021-11-18 | 2021-11-18
Coding | work on rewarding points | 2021-11-22 | 12:00 | 12:45 | 45 | 2021-11-22 | 2021-11-22
Coding | work on rewarding points and host interface | 2021-11-24 | 11:00 | 3:27 | 267 | 2021-11-24 | 2021-11-24
Team Agenda | participated in a team meeting | 2021-11-26 | 9:00 | 9:30 | 30 | 2021-11-26 | 2021-11-26
Team Agenda | participated in a client meeting | 2021-11-29 | 12:30 | 13:00 | 30 | 2021-11-29 | 2021-11-29
coding | incoperation new socket events and player Shuffle | 2021-11-30 | 9:30 | 12:50 | 200 | 2021-11-30 | 2021-11-30
coding | incoperation player shuffle | 2021-12-02 | 10:35 | 15:24 | 359 | 2021-12-02 | 2021-12-02
Team Agenda | participated in a team meeting | 2021-12-02 | 16:30 | 17:00 | 30 | 2021-12-02 | 2021-12-02
coding | fixing a bug and team lead faeture | 2021-12-04 | 11:45 | 14:35 | 170 | 2021-12-04 | 2021-12-04
design | creating an architecture for workflow | 2021-12-04 | 8:30 | 9:15 | 45 | 2021-12-04 | 2021-12-04
coding | fixing team leader feature | 2021-12-05 | 9:56 | 10:47 | 51 | 2021-12-05 | 2021-12-05
Team Agenda | participated in a client meeting | 2021-12-06 | 12:30 | 13:00 | 30 | 2021-12-06 | 2021-12-06
coding | adding additioanl in between interfaces | 2021-12-07 | 9:30 | 12:50 | 200 | 2021-12-07 | 2021-12-07
Team Agenda | participated in a team meeting | 2021-12-09 | 16:30 | 17:00 | 30 | 2021-12-09 | 2021-12-09
coding | fixing a bug and finish score board | 2021-12-10 | 18:50 | 5:08 | 618 | 2021-12-11 | 2021-12-11
Team Agenda | participated in a client meeting | 2022-01-20 | 10:30 | 11:30 | 60 | 2022-01-20 | 2022-01-20
Team Agenda | participated in a team meeting | 2022-01-20 | 10:00 | 10:30 | 30 | 2022-01-20 | 2022-01-20
Team Agenda | participated in a client meeting | 2022-01-27 | 10:30 | 11:30 | 60 | 2022-01-27 | 2022-01-27
Team Agenda | participated in a team meeting | 2022-01-27 | 10:00 | 10:30 | 30 | 2022-01-27 | 2022-01-27
coding | work on scoreboard | 2022-01-28 | 10:00 | 11:30 | 90 | 2022-01-28 | 2022-01-28
Team Agenda | participated in a client meeting | 2022-02-03 | 10:30 | 11:30 | 60 | 2022-02-03 | 2022-02-03
Team Agenda | participated in a team meeting | 2022-02-03 | 10:00 | 10:30 | 30 | 2022-02-03 | 2022-02-03
coding | styling of chat box and scoreboard | 2022-02-08 | 10:00 | 1:30 | 210 | 2022-02-08 | 2022-02-08
Team Agenda | participated in a client meeting | 2022-02-10 | 10:30 | 11:30 | 60 | 2022-02-10 | 2022-02-10
Team Agenda | participated in a team meeting | 2022-02-10 | 10:00 | 10:30 | 30 | 2022-02-10 | 2022-02-10
coding | styling player interface | 2022-02-15 | 10:00 | 3:30 | 330 | 2022-02-15 | 2022-02-15
Team Agenda | participated in a client meeting | 2022-02-17 | 10:30 | 10:05 | 5 | 2022-02-17 | 2022-02-17
Team Agenda | participated in a team meeting | 2022-02-17 | 10:00 | 10:30 | 30 | 2022-02-17 | 2022-02-17
Team Agenda | participated in a client meeting | 2022-02-24 | 10:30 | 10:05 | 60 | 2022-02-24 | 2022-02-24
Team Agenda | participated in a team meeting | 2022-02-24 | 10:00 | 10:30 | 30 | 2022-02-24 | 2022-02-24
Team Agenda | participated in a client meeting | 2022-03-03 | 10:30 | 10:05 | 60 | 2022-03-03 | 2022-03-03
Team Agenda | participated in a team meeting | 2022-03-03 | 10:00 | 10:30 | 30 | 2022-03-03 | 2022-03-03
coding | styling player interface | 2022-03-01 | 9:30 | 3:30 | 360 | 2022-03-01 | 2022-03-01
Team Agenda | participated in a client meeting | 2022-03-10 | 10:30 | 10:05 | 60 | 2022-03-10 | 2022-03-10
Team Agenda | participated in a team meeting | 2022-03-10 | 10:00 | 10:30 | 30 | 2022-03-10 | 2022-03-10
coding | fixing player interface | 2022-03-09 | 22:37 | 3:54 | 317 | 2022-03-09 | 2022-03-10
Team Agenda | participated in a client meeting | 2022-03-31 | 10:30 | 11:30 | 60 | 2022-03-31 | 2022-03-31
Team Agenda | participated in a team meeting | 2022-03-31 | 10:00 | 10:30 | 30 | 2022-03-31 | 2022-03-31
Team Agenda | participated in a client meeting | 2022-04-07 | 10:30 | 11:30 | 60 | 2022-04-07 | 2022-04-07
Team Agenda | participated in a team meeting | 2022-04-07 | 10:00 | 10:30 | 30 | 2022-04-07 | 2022-04-07
Team Agenda | participated in a client meeting | 2022-04-14 | 10:30 | 0:05 | 95 | 2022-04-14 | 2022-04-14
Team Agenda | participated in a team meeting | 2022-04-14 | 10:00 | 10:30 | 30 | 2022-04-14 | 2022-04-14
coding | fixing player interface | 2022-04-17 | 22:40 | 2:55 | 255 | 2022-04-17 | 2022-04-17
documentation | invitation | 2022-04-17 | 3:00PM | 3:20pm | 20 | 2022-04-17 | 2022-04-17
Team Agenda | Participated in a team meeting | 2022-04-21 | 10:00am | 10:30am | 30 | 2022-04-21 | 2022-04-21
Testing | Testing Social Comparison | 2022-04-23 | 10:00pm | 10:45pm | 45 | 2022-04-21 | 2022-04-23
Testing | Testing Lost and found | 2022-04-23 | 01:45pm | 02:30pm | 45 | 2022-04-24 | 2022-04-23
email | tech transfer | 2022-04-22 | 10:00am | 10:30am | 30 | 2022-04-21 | 2022-04-22
Team Agenda | participated in a client meeting | 2022-04-28 | 10:30 | 11:30 | 60 | 2022-04-28 | 2022-04-28
Team Agenda | participated in a team meeting | 2022-04-28 | 10:00 | 10:30 | 30 | 2022-04-28 | 2022-04-28

## Jason
Requirement | Task | Date | Start Time | End Time | Minutes Elape | Task Due Date | Task Actual Date Completed
Software Requirements Specifications | Examined the document and did research | 2021-09-08 | 08:35pm | 11:02pm | 147 | ASAP | 2021-09-27
Team Agenda | Participated in a meeting with clients | 2021-09-09 | 04:30pm | 05:04pm | 34 | 2021-09-09 | 2021-09-09
Software Requirements Specifications | Examined paper version of the game and other logistics tasks | 2021-09-13 | 11:00pm | 12:25pm | 55 | ASAP | 2021-09-27
Team Agenda | Participated in a meeting with clients | 2021-09-13 | 12:30pm | 01:02pm | 32 | 2021-09-13 | 2021-09-13
Team Agenda | Participated in a team meeting | 2021-09-16 | 03:41pm | 04:51pm | 70 | 2021-09-16 | 2021-09-16
Team Agenda | Participated in a meeting with clients | 2021-09-20 | 12:30pm | 01:10pm | 40 | 2021-09-20 | 2021-09-20
Software Requirements Specifications | Finished allocated part of the software requirements document | 2021-09-22 | 10:03pm | 12:15am | 122 | ASAP | 2021-09-27
Team Agenda | Participated in a meeting with clients | 2021-09-27 | 12:30pm | 01:02pm | 32 | 2021-09-27 | 2021-09-27
Team Agenda | Participated in a team meeting | 2021-09-30 | 04:30pm | 05:00pm | 30 | 2021-09-30 | 2021-09-30
Tech Stack Presentation | Did research on possible tech stack options | 2021-10-02 | 09:50pm | 10:40pm | 50 | 2021-10-04 | 2021-10-04
Tech Stack Presentation | Worked on tech stack presentation | 2021-10-04 | 12:01am | 01:15am | 74 | ASAP | 2021-10-04
Team Agenda | Participated in a meeting with clients | 2021-10-04 | 12:30pm | 01:00pm | 30 | 2021-10-04 | 2021-10-04
Team Agenda | Participated in a team meeting | 2021-10-07 | 04:30pm | 05:00pm | 30 | 2021-10-07 | 2021-10-07
Research | Did research on possible solutions for creating lobby-based web app | 2021-10-10 | 03:15pm | 05:49pm | 154 | ASAP | 2021-10-10
Coding | Coding a starting point for our lobby based web app | 2021-10-10 | 7:06pm | 9:07pm | 121 | ASAP | 2021-10-13
Coding | Coding a starting point for our lobby based web app | 2021-10-11 | 9:30am | 12:13pm | 163 | ASAP | 2021-10-13
Team Agenda | Participated in a meeting with clients | 2021-10-11 | 12:30am | 1:00pm | 30 | 2021-10-11 | 2021-10-11
Coding | Coding a starting point for our lobby based web app | 2021-10-12 | 1:30pm | 4:45pm | 195 | ASAP | 2021-10-13
Big rocks | Figuring out big rocks and roadmap | 2021-10-12 | 6:32pm | 7:40pm | 68 | 2021-10-12 | 2021-10-12
Coding | Coding a starting point for our lobby based web app | 2021-10-13 | 8:00pm | 10:00pm | 120 | ASAP | 2021-10-13
Deployment | Deployed code to Heroku | 2021-10-14 | 03:30pm | 04:28pm | 58 | 2021-10-14 | 2021-10-14
Team Agenda | Participated in a team meeting | 2021-10-14 | 04:30pm | 05:00pm | 30 | 2021-10-14 | 2021-10-14
Team Agenda | Participated in a meeting with clients | 2021-10-18 | 12:30pm | 01:21pm | 51 | 2021-10-18 | 2021-10-18
Github Setup | Set up GitHub | 2021-10-21 | 11:30am | 3:00pm | 210 | ASAP | 2021-10-21
Database Research | Did research on database hosting platform | 2021-10-21 | 3:00pm | 3:28pm | 28 | ASAP | 2021-10-21
Architecture Design | Drew graph for gameplay logic | 2021-10-21 | 3:28pm | 4:18pm | 50 | ASAP | 2021-10-21
Team Agenda | Participated in a team meeting | 2021-10-21 | 04:30pm | 05:00pm | 30 | 2021-10-21 | 2021-10-21
Team Agenda | Participated in a meeting with clients | 2021-10-25 | 12:30pm | 01:00pm | 30 | 2021-10-25 | 2021-10-25
Software Requirements Specifications | Wrote allocated part of the software requirements document | 2021-10-25 | 09:01pm | 11:28pm | 147 | ASAP | 2021-10-25
Software Requirements | Revision of section of requirements document | 2021-10-28 | 4:30am | 5:56pm | 86 | ASAP | 2021-10-28
Team Agenda | Participated in a meeting with clients | 2021-11-01 | 12:30pm | 01:00pm | 30 | 2021-11-01 | 2021-11-01
Coding | Coding | 2021-11-01 | 5:01pm | 6:02pm | 61 | ASAP | 2021-11-01
Coding | Coding | 2021-11-02 | 1:28am | 2:29am | 61 | ASAP | 2021-11-02
Coding | Coding | 2021-11-03 | 2:08pm | 3:58pm | 110 | ASAP | 2021-11-03
Coding | Coding | 2021-11-03 | 10:14pm | 01:50pm | 216 | ASAP | 2021-11-03
Coding | Coding | 2021-11-04 | 3:00pm | 4:06pm | 66 | ASAP | 2021-11-04
Team Agenda | Participated in a team meeting | 2021-11-04 | 4:30pm | 5:00pm | 30 | 2021-11-04 | 2021-11-04
Team Agenda | Participated in a meeting with clients | 2021-11-08 | 12:30pm | 01:00pm | 30 | 2021-11-08 | 2021-11-08
Coding | Database setup | 2021-11-09 | 05:30pm | 05:55pm | 25 | 2021-11-09 | 2021-11-09
Team Agenda | Participated in a team meeting | 2021-11-11 | 4:30pm | 5:00pm | 30 | 2021-11-11 | 2021-11-11
Coding | Coding | 2021-11-14 | 1:30pm | 5:06pm | 216 | ASAP | 2021-11-14
Coding | Coding | 2021-11-15 | 10:30pm | 12:15am | 105 | ASAP | 2021-11-16
Team Agenda | Participated in a meeting with clients | 2021-11-15 | 12:30pm | 01:00pm | 30 | 2021-11-15 | 2021-11-15
Coding | Coding | 2021-11-16 | 12:15pm | 4:00pm | 225 | ASAP | 2021-11-16
Coding | Coding | 2021-11-23 | 12:00pm | 1:00pm | 60 | ASAP | 2021-11-23
Coding | Coding | 2021-11-24 | 3:51pm | 6:00pm | 129 | ASAP | 2021-11-24
Coding | Coding | 2021-11-25 | 2:35pm | 5:00pm | 145 | ASAP | 2021-11-25
Team Agenda | Participated in a team meeting | 2021-11-26 | 9:00am | 9:30am | 30 | 2021-11-26 | 2021-11-26
Coding | Coding | 2021-11-26 | 3:24pm | 6:00pm | 156 | ASAP | 2021-11-26
Coding | Coding | 2021-11-27 | 9:45am | 12:00pm | 135 | ASAP | 2021-11-27
Coding | Coding | 2021-11-27 | 1:00pm | 4:30pm | 210 | ASAP | 2021-11-27
Coding | Coding | 2021-11-28 | 3:07pm | 4:35pm | 88 | ASAP | 2021-11-28
Team Agenda | Participated in a meeting with clients | 2021-11-29 | 12:30pm | 01:05pm | 35 | 2021-11-29 | 2021-11-29
Coding | Coding | 2021-12-01 | 02:30pm | 04:15pm | 105 | ASAP | 2021-12-01
Team Agenda | Participated in a team meeting | 2021-12-01 | 04:30pm | 05:00pm | 30 | 2021-12-01 | 2021-12-01
Coding | Coding | 2021-12-05 | 2:30pm | 6:00pm | 210 | ASAP | 2021-12-05
Coding | Coding | 2021-12-05 | 10:00pm | 12:03pm | 123 | ASAP | 2021-12-05
Team Agenda | Participated in a meeting with clients | 2021-12-06 | 12:30pm | 01:05pm | 35 | 2021-12-06 | 2021-12-06
Coding | Coding | 2021-12-07 | 11:19am | 4:30pm | 311 | ASAP | 2021-12-07
Coding | Coding | 2021-12-07 | 8:00pm | 11:46pm | 226 | ASAP | 2021-12-07
Coding | Coding | 2021-12-08 | 11:05am | 2:30pm | 205 | ASAP | 2021-12-08
Coding | Coding | 2021-12-08 | 08:12pm | 11:20pm | 188 | ASAP | 2021-12-08
Coding | Coding | 2021-12-09 | 09:45am | 4:00pm | 375 | ASAP | 2021-12-09
Team Agenda | Participated in a team meeting | 2021-12-09 | 04:30pm | 05:00pm | 30 | 2021-12-09 | 2021-12-09
Coding | Coding | 2021-12-09 | 11:00pm | 12:00pm | 60 | ASAP | 2021-12-09
Coding | Coding | 2021-12-11 | 11:00am | 3:00pm | 240 | ASAP | 2021-12-11
Coding | Coding | 2021-12-12 | 11:00am | 2:00am | 900 | ASAP | 2021-12-12
Coding | Coding | 2021-12-13 | 8:40am | 12:30pm | 230 | ASAP | 2021-12-13
Team Agenda | Participated in a meeting with clients | 2021-12-13 | 12:30pm | 01:15pm | 45 | 2021-12-13 | 2021-12-13
Coding | Coding | 2021-12-13 | 5:00pm | 6:20pm | 80 | ASAP | 2021-12-13
Coding | Coding | 2021-12-13 | 8:40pm | 11:00pm | 140 | ASAP | 2021-12-13
Coding | Coding | 2021-12-14 | 9:40am | 2:11pm | 271 | ASAP | 2021-12-14
Team Agenda | Participated in a team meeting | 2022-01-27 | 10:00am | 10:30am | 30 | 2022-01-27 | 2022-01-27
Team Agenda | Participated in a meeting with clients | 2022-01-27 | 10:30am | 11:30am | 60 | 2022-01-27 | 2022-01-27
Debugging | Debugging | 2022-01-30 | 07:03pm | 08:05pm | 62 | 2022-01-30 | 2022-01-30
Team Agenda | Participated in a team meeting | 2022-02-03 | 10:00am | 10:30am | 30 | 2022-02-03 | 2022-02-03
Team Agenda | Participated in a meeting with clients | 2022-02-03 | 10:30am | 11:30am | 60 | 2022-02-03 | 2022-02-03
Debugging | Debugging | 2022-02-04 | 07:03pm | 11:05pm | 182 | 2022-02-04 | 2022-02-04
Debugging | Debugging | 2022-02-09 | 05:50pm | 07:20pm | 90 | 2022-02-09 | 2022-02-04
Team Agenda | Participated in a team meeting | 2022-02-10 | 10:00am | 10:30am | 30 | 2022-02-10 | 2022-02-10
Team Agenda | Participated in a meeting with clients | 2022-02-10 | 10:30am | 11:30am | 60 | 2022-02-10 | 2022-02-10
Debugging | Debugging | 2022-02-12 | 9:17am | 10:30am | 73 | 2022-02-12 | 2022-02-12
Team Agenda | Participated in a team meeting | 2022-02-17 | 10:00am | 10:30am | 30 | 2022-02-17 | 2022-02-17
Team Agenda | Participated in a meeting with clients | 2022-02-17 | 10:30am | 11:30am | 60 | 2022-02-17 | 2022-02-17
Debugging | Debugging | 2022-02-16 | 10:59am | 12:02pm | 63 | 2022-02-16 | 2022-02-16
Adding Features | Adding Features | 2022-02-19 | 05:00pm | 06:30pm | 90 | 2022-02-19 | 2022-02-19
Team Agenda | Participated in a team meeting | 2022-02-24 | 10:00am | 10:30am | 30 | 2022-02-24 | 2022-02-24
Team Agenda | Participated in a meeting with clients | 2022-02-24 | 10:30am | 11:30am | 60 | 2022-02-24 | 2022-02-24
Adding Features | Adding Features | 2022-02-24 | 03:00pm | 03:52pm | 52 | 2022-02-24 | 2022-02-24
Adding Features | Adding Features | 2022-02-27 | 04:00pm | 05:32pm | 92 | 2022-02-27 | 2022-02-27
Team Agenda | Participated in a team meeting | 2022-03-03 | 10:00am | 10:30am | 30 | 2022-03-03 | 2022-03-03
Team Agenda | Participated in a meeting with clients | 2022-03-03 | 10:30am | 11:30am | 60 | 2022-03-03 | 2022-03-03
Adding Features | Adding Features | 2022-03-04 | 03:00pm | 07:00pm | 240 | 2022-03-04 | 2022-03-04
Adding Features | Adding Features | 2022-03-06 | 12:51pm | 05:46pm | 295 | 2022-03-06 | 2022-03-06
Adding Features | Adding Features | 2022-03-07 | 07:00pm | 09:00pm | 120 | 2022-03-07 | 2022-03-07
Adding Features | Adding Features | 2022-03-08 | 12:30pm | 3:00pm | 150 | 2022-03-08 | 2022-03-08
Adding Features | Adding Features | 2022-03-09 | 02:03pm | 06:00pm | 237 | 2022-03-09 | 2022-03-09
Adding Features | Adding Features | 2022-03-09 | 07:00pm | 12:40pm | 340 | 2022-03-09 | 2022-03-09
Team Agenda | Participated in a team meeting | 2022-03-10 | 09:15am | 09:45am | 30 | 2022-03-10 | 2022-03-10
Team Agenda | Participated in a meeting with clients | 2022-03-10 | 09:45am | 11:30am | 105 | 2022-03-10 | 2022-03-10
Teammate Survey | Filling out teammate survey | 2022-03-12 | 05:20pm | 06:30pm | 70 | 2022-03-12 | 2022-03-12
Testing | Testing HuFit | 2022-03-14 | 12:55pm | 02:20pm | 85 | 2022-03-14 | 2022-03-14
Testing | Testing Social Comparison | 2022-03-29 | 08:00pm | 09:00pm | 60 | 2022-03-29 | 2022-03-29
Team Agenda | Creating Agenda and PowerPoint | 2022-03-30 | 08:00pm | 12:00am | 240 | 2022-03-30 | 2022-03-30
Team Agenda | Participated in a team meeting | 2022-03-31 | 10:00am | 10:30am | 30 | 2022-03-31 | 2022-03-31
Team Agenda | Participated in a meeting with clients | 2022-03-31 | 10:30am | 11:30am | 60 | 2022-03-31 | 2022-03-31
Team Agenda | Participated in a team meeting | 2022-03-31 | 11:30am | 12:00pm | 30 | 2022-03-31 | 2022-03-31
Team Agenda | Emails | 2022-03-31 | 2:00pm | 04:30pm | 150 | 2022-03-31 | 2022-03-31
Bug Fixing | Fixing high priority bugs | 2022-04-06 | 01:00pm | 04:30pm | 210 | 2022-04-06 | 2022-04-06
Team Agenda | Participated in a team meeting | 2022-04-07 | 10:00am | 10:30am | 30 | 2022-04-07 | 2022-04-07
Team Agenda | Participated in a meeting with clients | 2022-04-07 | 10:30am | 11:30am | 60 | 2022-04-07 | 2022-04-07
Team Agenda | Emails | 2022-04-07 | 3:00pm | 04:00pm | 60 | 2022-04-07 | 2022-04-07
Bug Fixing | Fixing high priority bugs | 2022-04-08 | 02:30pm | 04:50pm | 140 | 2022-04-08 | 2022-04-08
Bug Fixing | Fixing high priority bugs | 2022-04-08 | 07:25pm | 11:02pm | 217 | 2022-04-08 | 2022-04-08
Bug Fixing | Fixing high priority bugs | 2022-04-09 | 12:02pm | 03:30pm | 208 | 2022-04-09 | 2022-04-09
Bug Fixing | Fixing Additional Bugs | 2022-04-13 | 8:22pm | 10:30pm | 108 | 2022-04-13 | 2022-04-13
Team Agenda | Emails | 2022-04-13 | 2:00pm | 03:00pm | 60 | 2022-04-13 | 2022-04-13
Bug Fixing | Fixing Additional Bugs | 2022-04-14 | 06:45am | 10:00am | 195 | 2022-04-14 | 2022-04-14
Team Agenda | Participated in a team meeting | 2022-04-14 | 10:00am | 10:30am | 30 | 2022-04-14 | 2022-04-14
Team Agenda | Participated in a meeting with clients | 2022-04-14 | 10:30am | 12:05pm | 95 | 2022-04-14 | 2022-04-14
Team Agenda | Emails | 2022-04-14 | 12:05pm | 12:50pm | 45 | 2022-04-14 | 2022-04-14
Bug Fixing | Fixing Additional Bugs | 2022-04-16 | 01:00pm | 07:20pm | 380 | 2022-04-16 | 2022-04-16
Team Agenda | Participated in a team meeting | 2022-04-21 | 10:00am | 10:30am | 30 | 2022-04-21 | 2022-04-21
Testing | Testing Social Comparison | 2022-04-21 | 08:00pm | 08:45pm | 45 | 2022-04-21 | 2022-04-21
Testing | Testing HuFit | 2022-04-24 | 01:46pm | 02:30pm | 44 | 2022-04-24 | 2022-04-24
Team Agenda | Participated in a team meeting | 2022-04-28 | 10:00am | 10:30am | 30 | 2022-04-28 | 2022-04-28
Team Agenda | Participated in a meeting with clients | 2022-04-28 | 10:30am | 11:30am | 60 | 2022-04-28 | 2022-04-28
Documentation | Write a note on setting up local server | 2022-04-28 | 06:00pm | 07:30pm | 90 | 2022-04-28 | 2022-04-28